“A member of the IDC group of Companies”

Internal Audit Follow-up Log Report submitted to the Executive Committee and Management of INFRATEL Corporation Limited

31st January 2025

Monthly Report

# Executive Summary

The report highlights the outstanding audit issues resulting from prior audits performed by internal and external audit assurance providers.

During the month of January 2025, the audit issue closure completion rate stood at 91% representing 230 closed issues out of 252.

The department continued to actively support the business through monthly follow-up of              open items and the validation of supporting evidence for closure.

# Purpose

The purpose of Internal Audit follow-ups is to ensure that management has adequately addressed and implemented the recommendations made in previous internal and external audit reports. Follow-ups are conducted to:

- Verify Implementation: Confirm that corrective actions have been taken to address the findings and risks identified during the initial audit including root cause analysis.

- Assess Effectiveness: Evaluate whether the implemented actions have effectively mitigated the risks or issues highlighted.

- Monitor Compliance: Ensure that policies, procedures, and regulatory requirements are being adhered to after the recommendations are acted upon.

- Promote Accountability: Hold responsible parties accountable for addressing the audit findings within the agreed timeframes.

- Continuous Improvement: Identify any further actions or improvements required to enhance controls, processes, and risk management.

Table 1: Corrective Action Summary as of 31st January 2024

| Corrective Action Summary as of 31 January 2025 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Category | On Target | 30 days Past due | 60 days Past due | 90 days Past due | 180 days Past due | Total issues Closed to date (-) | Total Unresolved Issues | Total |
| Internal Audit Issues | 0 | 2 | 1 | 2 | 4 | 124 | 9 | 133 |
| IDC Group Audit Issues | 0 | 0 | 0 | 0 | 0 | 14 | - | 14 |
| Auditor General Issues | 3 | 0 | 0 | 0 | 0 | 56 | 3 | 59 |
| External Audit Issues | 2 | 5 | 1 | 0 | 2 | 31 | 10 | 41 |
| ZICTA Regulatory Issues | 0 | 0 | 0 | 0 | 0 | 5 | - | 5 |
| TOTAL | 5 | 6 | 2 | 2 | 6 | 230 | 22 | 252 |

Table 1 above highlights audit issues which are on target and those that are past 180 days due.

Accordingly, the report highlights (5) issues on target, (6) 30 days past due, (2) 60 days past due, (2) 90 days past due and (6) being 180 days past due.

Figure 1: Closure rate status of Outstanding Audit Issues

| Current Status with new issues. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| AUDIT CATEGORY | OPEN | CLOSED | TOTAL | TARGET % | % Closure Rate |
| INTERNAL AUDIT | 9 | 124 | 133 | 90% | 93% |
| EXTERNAL AUDIT-FINANCE ISSUES | 10 | 31 | 41 | 90% | 76% |
| GROUP AUDIT IDC | 0 | 14 | 14 | 90% | 100% |
| AUDITOR GENERAL ISSUES | 3 | 56 | 59 | 90% | 95% |
| ZICTA | 0 | 5 | 5 | 90% | 100% |
| TOTAL | 22 | 230 | 252 | 90% | 91% |

The figure above as well as the table, indicates the closure rate in terms of categories.

- Internal Audit Issues had a closure rate of 93% representing 124 closed out of 133,

- External Audit issues had a closure rate of 90%, indicating that 31 of 41 issues were closed,

- Group Audit (IDC) issues stand at 100% closure, indicating that 14 of 14 issues were closed,

- ZICTA stands at 100% closure, indicating that 5 of 5 issues were closed,

- Auditor General at 95% closure rate, indicating that 56 of 59 issues were closed,

Table 2: Summary of unresolved issues above 180 days past due

| NO. | ISSUE | DAYS OVERDUE | ASSURANCE TYPE | STATUS | MANAGEMENT CORRECTIVE STATUS |
| --- | --- | --- | --- | --- | --- |
| 1 | Customer Contracts Lack of Customer contracts as per sample by Deloitte and Internal Audit, we noted that Infratel did not have contracts for services rendered | 1127 | Deloitte External | Open | An online contract Database with all contracts has been created to enable easy access of contracts and dates they expire. The customer base is 400, out of these, 396 have valid contracts. |
| 2 | Management of fixed assets 1. Residual value assessment of fixed assets We noted that the Company does not carry out an assessment of the reasonableness of residual values of some of its classes of fixed assets. 2. Coding of fixed assets Fixed asset items physically verified were not easily matched to their respective line items on the fixed asset register as the entity does not have tagging system in place to ensure that the assets of the entity are labelled with unique identifiers. 3. Regula fixed asset physical verification We noted that the Company does not perform regular physical asset verifications of all fixed assets. This resulted in the following issues that were identified during our fixed asset physical verification exercise: > Missing assets > Damaged assets still recognized in full in the fixed asset register > Assets included under the Infratel fixed asset register but still belonged to ZAMTEL > Assets not in a working condition | 1096 | Deloitte External | Open | 1. The residue value exercise was not carried out due to the fact that there was no complete fixed asset register. 2. Coding of fixed assets was completed in all the provinces. Audit to validate via a report and close the issue |
| 3 | DECOMMISSIONED EQUIPMENT Our review revealed that 13 of 59 (22%) of sites visited had equipment requiring decommissioning Out of Service Assets still appearing on the Fixed Asset Register Our audit revealed 119 of 663 assets which were assessed as out of service with a total Net Book Value of ZMW 377,098.62 for Central and Lusaka provinces. Our audit revealed a few assets that were physically on tower sites, but they were non-functional, or they required to be worked on with an estimated Net Book Value (NBV) as of April 2022 of ZMW 70, 618.85 | 762 | Internal Audit | Open | A list of decommissioned equipment was shared with the Disposal Committee as well as Internal Audit & Risk for Validation. Internal Audit & Risk to engage with Chairperson for the Committee to obtain targets date for closure. Internal Audit did engage with Chairperson for the Asset Disposal Committee and the indicated that the Committee will meet in the fourth week of January 2024 to plan on how the exercise of disposal will be executed as well validation process. Further, he indicated before end of Q2 2024, Disposal of approved assets will be carried out. HCA indicated that the meeting wasn't held as discussed in the last meeting, but the meeting with Asset Disposal Committee is scheduled to take place in July 2024. A list of assets to be disposed off was compiled and shared with Audit team for verification purposes. However, the disposal process will delay due to the following processes which needs to be completed first: 1. Completion of asset tagging exercise 2. engagement of the valuator 3. Board paper for the approval of assets to be disposed off. > Disposal of assets will be done first in Lusaka and part of Southern Province. > The valuator was engaged and the valuation process commenced > The Board paper for the approval of assets to be disposed off will only be done after the valuation process has finished and the report done. The valuation was done and draft report was issued to the Committee by 28th February the report will be presented to EXCO. The actual disposal of assets will be commenced before end of Q1 2025 after the approval by the Board. |
| 4 | LACK OF PERIODIC INVENTORY COUNTS. We noted that the INFRATELS Procurement and Stores Manual does not include measures to ensure that goods in stores do not deteriorate from any preventable causes as further validated for a lack of documented inventory count process and the actual occurrence of an inventory count | 762 | Internal Audit | Open | The inventory count was carried out and final report to be shared by CFO. CFO shared final report to HSC with some come comments concerning a discrepancy in the system in relation the updates. HSC addressed the discrepancies in the system and the need for validation from a consultant before sharing the final report. This issue will be closed once the physical inventory count is done before end of July 2024. Finance dept will share the report once the Q3 2024 inventory is concluded and procedures will be devised at month end of October 2024. The stock take report for October 2024 was submitted to Internal Audit for validation, however, a Q4 stock take report will be submitted for the closure of the issue |
| 5 | NON-EXISTENCE OF FIXED ASSETS ON TOWER SITES Our audit of the asset verification exercise revealed 30 of 800 (4%) assets that could not be located on 66 tower sites in Copperbelt and North-western provinces with a total Net Book Value of ZMW 780,715.49 | 397 | Internal Audit | Open | Asset verification and tagging exercise is on-going and scheduled to be completed by 31st December 2024 The clean-up of all non-existence and non-working assets will be carried out in respect to decommissioning of equipment exercise by Disposal committee. The asset tagging report to be shared for the closure of this issue. |
| 6 | NON-REVIEW OF EXECUTED LEASES Our audit revealed that 5 of 44 (11%) leases based on a sample were not reviewed and updated to reflect the current rebased currency position as they still reflected the old un-rebased amounts. Accordingly, it was noted that 1 of 44 (2%) leases was expired (SOP0016-VICTORIA FALLS). | 184 | Internal Audit | Open | An engagement was carried between Legal and Technical. To resolve this issue, Technical has resolved that data collection on leases needs to be conducted to establish the actual database as well as considering issues such as currency, period and thereafter, review of leases to be carried. The above exercise on data collection was planned be closed by February 2024. However, considering how involving the exercise is, Technical under projects did request for a temporal employee to assist in completing this task. The request to recruit temp was denied as approval to employ permanent Project Officer was given, technical is currently waiting for the new staff member to report for speedy progress can be made on this issue. 189 leases of 569 were updated representing 33% completion rate. |
| Average Overdue days |  | 722 |  |  |  |

SUBMITTED FOR YOUR CONSIDERATION.

Mwenya S. Zulu

Head – Internal Audit & Risk